# Low Cost Air Quality Monitor System – Engineering Design Processes

## Requirement Engineering

| Activity | Input | Tools/Method | Critical Parameter | Output |
| --- | --- | --- | --- | --- |
| Identify problem | Problem statement | Stakeholder interview | Accuracy | Problem definition |
| Collect requirements | User needs | Survey | Completeness | Requirement list |
| Define parameters | Standards | Literature study | Relevance | Parameter list |
| Analyze requirements | Requirements | Analysis | Feasibility | Refined requirements |
| Review requirements | Draft requirements | Review meeting | Clarity | Approved requirements |
| Freeze requirements | Final requirements | Approval | Stability | SRS |

## Concept Design

| Activity | Input | Tools/Method | Critical Parameter | Output |
| --- | --- | --- | --- | --- |
| Generate concepts | SRS | Brainstorming | Innovation | Concept ideas |
| Evaluate concepts | Concept ideas | Pugh matrix | Feasibility | Ranked concepts |
| Select concept | Ranked concepts | Decision matrix | Cost | Selected concept |
| Prepare block diagram | Concept | Block diagram | Functionality | System block |
| Concept validation | Block diagram | Review | Logic | Validated concept |
| Freeze concept | Validated concept | Approval | Stability | Concept document |

## Embodiment Design

| Activity | Input | Tools/Method | Critical Parameter | Output |
| --- | --- | --- | --- | --- |
| Define architecture | Concept | System modeling | Integration | Architecture |
| Select sensors | Architecture | Comparison | Accuracy | Sensor selection |
| Select controller | Architecture | Benchmarking | Performance | Controller |
| Layout design | Components | CAD | Space | Layout |
| Verify layout | Layout | Review | Ergonomics | Verified layout |
| Freeze embodiment | Verified layout | Approval | Stability | Embodiment design |

## Detail Design

| Activity | Input | Tools/Method | Critical Parameter | Output |
| --- | --- | --- | --- | --- |
| Detail drawings | Embodiment | CAD | Dimension | Drawings |
| Tolerance analysis | Drawings | Analysis | Fit | Tolerance data |
| Material selection | Design | Material chart | Strength | Material list |
| Design review | Design | Review | Errors | Corrected design |
| Update drawings | Review | CAD | Accuracy | Updated drawings |
| Freeze detail design | Final drawings | Approval | Stability | Detail design |

## Sourcing

| Activity | Input | Tools/Method | Critical Parameter | Output |
| --- | --- | --- | --- | --- |
| Prepare BOM | Design | BOM tool | Completeness | BOM |
| Identify suppliers | BOM | Market survey | Availability | Supplier list |
| Cost estimation | Supplier data | Cost analysis | Budget | Cost sheet |
| Purchase parts | Approved list | Procurement | Delivery | Components |
| Inspection | Received parts | Inspection | Quality | Accepted parts |
| Sourcing approval | Inspected parts | Approval | Quality | Ready components |

## Prototype Building

| Activity | Input | Tools/Method | Critical Parameter | Output |
| --- | --- | --- | --- | --- |
| Plan assembly | Components | Planning | Sequence | Assembly plan |
| Prepare tools | Plan | Tool setup | Availability | Tools ready |
| Assemble prototype | Parts | Assembly | Accuracy | Prototype |
| Wiring & integration | Prototype | Integration | Safety | Integrated unit |
| Initial check | Unit | Testing | Function | Checked prototype |
| Build approval | Checked unit | Approval | Stability | Ready prototype |

## Prototype Testing

| Activity | Input | Tools/Method | Critical Parameter | Output |
| --- | --- | --- | --- | --- |
| Test planning | Prototype | Test plan | Coverage | Test cases |
| Calibration | Sensors | Calibration | Accuracy | Calibrated system |
| Functional testing | System | Testing | Response | Test data |
| Performance testing | System | Measurement | Reliability | Performance data |
| Data analysis | Test data | Analysis | Validity | Results |
| Test approval | Results | Review | Acceptance | Approved testing |

## Iteration & Optimization

| Activity | Input | Tools/Method | Critical Parameter | Output |
| --- | --- | --- | --- | --- |
| Identify gaps | Results | Gap analysis | Impact | Improvement list |
| Redesign | Gaps | Design iteration | Efficiency | Modified design |
| Implement changes | Design | Modification | Accuracy | Updated system |
| Retesting | System | Testing | Consistency | New results |
| Fine tuning | Results | Optimization | Performance | Optimized system |
| Freeze optimized design | Optimized system | Approval | Stability | Final design |

## Documentation & Sharing

| Activity | Input | Tools/Method | Critical Parameter | Output |
| --- | --- | --- | --- | --- |
| Identify documents | Project data | Checklist | Completeness | Doc list |
| Prepare report | Data | Documentation | Clarity | Draft report |
| Prepare drawings | Design | CAD | Accuracy | Final drawings |
| Review documents | Drafts | Review | Errors | Corrected docs |
| Finalize documents | Reviewed docs | Formatting | Standard | Final report |
| Submission | Final report | Submission | Compliance | Project completion |

## List of Activity

## 1. REQUIREMENT ENGINEERING

- Identify the air quality problem and define the project objective

- Collect user and stakeholder requirements

- Identify measurable air quality parameters (PM2.5, PM10, gases)

- Define system-level functional and non-functional requirements

- Review and refine requirements for feasibility and cost

- Freeze and approve the final requirement specification

## 2. CONCEPT DESIGN

- Generate multiple concepts for low-cost air quality monitoring

- Compare concepts based on cost, accuracy, and simplicity

- Develop block diagrams for shortlisted concepts

- Evaluate concepts against performance criteria

- Improve the selected concept based on evaluation feedback

- Freeze the final concept design

## 3. EMBODIMENT DESIGN

- Define the overall system architecture

- Select suitable sensors, controller, and communication modules

- Design the physical layout and airflow path for sensors

- Verify component placement and interface compatibility

- Optimize the layout for compactness and low power usage

- Freeze the embodiment design

## 4. DETAIL DESIGN

- Define the scope of detailed mechanical and electrical design

- Prepare detailed component specifications and tolerances

- Create detailed circuit schematics and enclosure drawings

- Review detailed drawings for errors and compliance

- Correct design issues and update drawings

- Release final detailed design for procurement and build

## 5. SOURCING

- Prepare the bill of materials (BOM)

- Identify and shortlist component suppliers

- Purchase required sensors, electronics, and materials

- Inspect received components for quality and specification match

- Resolve non-conformities through replacement or rework

- Approve sourced components for prototype build

## 6. PROTOTYPE BUILDING

- Plan the prototype build sequence and assembly process

- Prepare tools, workspace, and safety arrangements

- Assemble electronic circuits and mechanical enclosure

- Inspect the assembled prototype for fit and stability

- Rework and correct assembly issues

- Finalize the functional prototype for testing

## 7. PROTOTYPE TESTING

- Prepare the test plan and define performance criteria

- Set up calibration and testing environment

- Conduct air quality measurement tests

- Analyze test data and compare with expected results

- Identify faults, errors, and performance gaps

- Approve prototype performance or recommend improvements

## 8. ITERATION FOR OPTIMIZATION

- Identify areas requiring improvement based on test results

- Select optimization techniques for accuracy and power reduction

- Implement design and firmware improvements

- Retest the optimized system

- Fine-tune system parameters and settings

- Freeze the optimized design

## 9. DOCUMENTING FOR SHARING

- Identify required project documents and deliverables

- Organize technical data, drawings, and test results

- Prepare the complete project report

- Review documentation for clarity and completeness

- Finalize and correct the project documentation

- Submit and share the final project materials

Activity Duration Table

| S.No | Activity Description | Duration (Hours) |
| --- | --- | --- |
| 1 | Identify air quality problem & objectives | 3 |
| 2 | Collect user & stakeholder requirements | 4 |
| 3 | Identify air quality parameters | 3 |
| 4 | Define system requirements | 4 |
| 5 | Review & refine requirements | 3 |
| 6 | Freeze requirement specification | 3 |
| 7 | Generate concept ideas | 4 |
| 8 | Compare concepts | 4 |
| 9 | Develop concept block diagrams | 4 |
| 10 | Evaluate concepts | 4 |
| 11 | Improve selected concept | 3 |
| 12 | Freeze concept design | 3 |
| 13 | Define system architecture | 4 |
| 14 | Select sensors & controller | 5 |
| 15 | Design physical layout | 5 |
| 16 | Verify layout | 4 |
| 17 | Optimize layout | 4 |
| 18 | Freeze embodiment design | 4 |
| 19 | Define detail design scope | 4 |
| 20 | Prepare part specifications | 5 |
| 21 | Create detailed drawings | 6 |
| 22 | Review drawings | 4 |
| 23 | Correct drawings | 4 |
| 24 | Release detailed design | 3 |
| 25 | Prepare bill of materials | 3 |
| 26 | Identify suppliers | 4 |
| 27 | Purchase components | 4 |
| 28 | Inspect received components | 4 |
| 29 | Resolve sourcing issues | 3 |
| 30 | Approve sourced components | 3 |
| 31 | Plan prototype build | 3 |
| 32 | Prepare tools & setup | 3 |
| 33 | Assemble prototype | 6 |
| 34 | Inspect prototype | 4 |
| 35 | Rework prototype | 4 |
| 36 | Finalize prototype | 3 |
| 37 | Prepare test plan | 3 |
| 38 | Setup test environment | 3 |
| 39 | Conduct testing | 5 |
| 40 | Analyze test data | 4 |
| 41 | Identify faults | 3 |
| 42 | Approve test results | 2 |
| 43 | Identify optimization areas | 3 |
| 44 | Select optimization method | 2 |
| 45 | Implement improvements | 4 |
| 46 | Retest optimized system | 3 |
| 47 | Fine tuning | 2 |
| 48 | Freeze optimized design | 2 |
| 49 | Identify documentation needs | 2 |
| 50 | Organize technical content | 2 |
| 51 | Prepare project report | 3 |
| 52 | Review documentation | 2 |
| 53 | Final corrections | 2 |
| 54 | Submit & share project | 1 |
| TOTAL |  | 200 HOURS |

ACTIVITY PRECEDENCE TABLE

| Activity No. | Activity Description (Short) | Immediate Predecessor(s) |
| --- | --- | --- |
| 1 | Identify problem & objectives | — |
| 2 | Collect user requirements | 1 |
| 3 | Identify AQ parameters | 2 |
| 4 | Define system requirements | 3 |
| 5 | Review requirements | 4 |
| 6 | Freeze requirements | 5 |
| 7 | Generate concepts | 6 |
| 8 | Compare concepts | 7 |
| 9 | Develop concept diagrams | 8 |
| 10 | Evaluate concepts | 9 |
| 11 | Improve concept | 10 |
| 12 | Freeze concept | 11 |
| 13 | Define system architecture | 12 |
| 14 | Select sensors & controller | 13 |
| 15 | Design physical layout | 14 |
| 16 | Verify layout | 15 |
| 17 | Optimize layout | 16 |
| 18 | Freeze embodiment design | 17 |
| 19 | Define detail design scope | 18 |
| 20 | Prepare part specifications | 19 |
| 21 | Create detailed drawings | 20 |
| 22 | Review drawings | 21 |
| 23 | Correct drawings | 22 |
| 24 | Release detailed design | 23 |
| 25 | Prepare BOM | 24 |
| 26 | Identify suppliers | 25 |
| 27 | Purchase components | 26 |
| 28 | Inspect components | 27 |
| 29 | Resolve sourcing issues | 28 |
| 30 | Approve sourced components | 29 |
| 31 | Plan prototype build | 30 |
| 32 | Prepare tools & setup | 31 |
| 33 | Assemble prototype | 32 |
| 34 | Inspect prototype | 33 |
| 35 | Rework prototype | 34 |
| 36 | Finalize prototype | 35 |
| 37 | Prepare test plan | 36 |
| 38 | Setup test environment | 37 |
| 39 | Conduct testing | 38 |
| 40 | Analyze test data | 39 |
| 41 | Identify faults | 40 |
| 42 | Approve test results | 41 |
| 43 | Identify optimization areas | 42 |
| 44 | Select optimization method | 43 |
| 45 | Implement improvements | 44 |
| 46 | Retest optimized system | 45 |
| 47 | Fine tuning | 46 |
| 48 | Freeze optimized design | 47 |
| 49 | Identify documentation needs | 48 |
| 50 | Organize documentation content | 49 |
| 51 | Prepare project report | 50 |
| 52 | Review documentation | 51 |
| 53 | Final corrections | 52 |
| 54 | Submit & share project | 53 |

Activity Network Diagram